# Test Plan Template

A short, practical test plan for one release. Fill it in, share it with your team, and get it signed off before testing starts.

| Project | e.g. Food delivery app (Android, iOS and web) |
| --- | --- |
| Version | Release or build this plan covers, e.g. 2.4 |
| Prepared by | Name, role |
| Reviewed by | Name, role |
| Date | DD-MM-YYYY |
| Status | ☐ Draft ☐ Approved |

How to use Grey italic lines tell you what to write in each section. Yellow boxes and yellow table cells show an example for a "Food delivery app, release 2.4". Replace them with your own project details, then delete the hints. Keep it short. A plan people actually read beats a long one nobody opens.

# 1. Purpose

In 2 or 3 lines, say what this plan covers and why it exists.

Example: This plan explains how we will test release 2.4 of the food delivery app. The release adds scheduled orders, a "Reorder" button and UPI autopay. It tells the team what we test, how we test it, who does what, and when testing is done.

# 2. Scope

List what you will test and what you will not test. For each out of scope item, give a reason.

## In scope

| Feature / module | What we will check |
| --- | --- |
| Scheduled orders | Pick a delivery slot, edit it, cancel it, reminder notification |
| Reorder button | Reorder from order history, item out of stock, restaurant closed |
| UPI autopay | Set up, pay, payment failure, cancel autopay |

## Out of scope

| Feature / module | Reason |
| --- | --- |
| Restaurant partner app | Separate release, tested by the partner app team |
| Full load testing | Planned for release 2.5. Only a performance smoke check in this release. |

# 3. Test approach

For each type of testing, say what you will do and how (manual or automated, and which tool). Remove types you will not run.

| Type of testing | What we will do | How |
| --- | --- | --- |
| Functional | Test new features against user stories. Positive and negative cases. | Manual, test cases in Excel or TestRail |
| Regression | Check that login, search, cart, payment and order tracking still work | Automated suite (Selenium) plus manual smoke test |
| API | Order, slot and payment APIs: status codes, response fields, error messages | Postman collection |
| UI | Layout, text, buttons and images on small and large screens | Manual, compared with Figma designs |
| Compatibility | Android 12 to 15, iOS 17 and 18, Chrome and Safari on web | Real devices plus BrowserStack |
| Performance smoke | Menu load time and checkout response on a normal 4G connection | Basic JMeter run, results compared with release 2.3 |
| Exploratory | Short time-boxed sessions on the new features | Manual, notes in a session sheet |

# 4. Test environment

Where will you test? Give the URL or build, the browsers and devices, and where test data comes from.

| Environment | URL / build | Browsers / devices | Test data source |
| --- | --- | --- | --- |
| QA | qa.fooddelivery.example.com, Android build 2.4.0-qa | Chrome, Firefox, Pixel 7 (Android 14), iPhone 13 (iOS 18) | Seed script with test users and test restaurants |
| Staging | staging.fooddelivery.example.com | Same as QA, plus Safari | Masked copy of production data |

# 5. Entry criteria

When can testing start? Write clear conditions that anyone can check.

Example: - Build 2.4 is deployed on QA and the smoke test passed. - User stories and acceptance criteria are final. - Test cases are written and reviewed. - Test accounts, test restaurants and payment sandbox are ready.

# 6. Exit criteria

When can testing stop? Use points that can be measured, not feelings.

Example: - All planned test cases are run, and results are recorded. - No open Critical or Major bugs. - Open Minor and Trivial bugs are reviewed and accepted by the product owner. - Regression suite passed on the final build. - Test summary report is shared with the team.

# 7. Roles and responsibilities

Who does what? Add a name for each role. Change the duties to match your team.

| Name | Role | Responsibilities |
| --- | --- | --- |
|  | QA lead | Writes this plan, reviews test cases, shares daily status, gives QA sign-off |
|  | QA engineer | Writes and runs test cases, logs bugs, retests fixes |
|  | Developer | Fixes bugs, shares build notes, helps with test data |
|  | Product owner | Answers requirement questions, accepts known issues, final sign-off |

# 8. Schedule

List the main milestones with dates and an owner. Keep some buffer before the release date.

| Milestone | Start | End | Owner |
| --- | --- | --- | --- |
| Test planning and test case writing | 02-11-2026 | 06-11-2026 | QA lead |
| Test execution, cycle 1 | 09-11-2026 | 13-11-2026 | QA team |
| Bug fixing and retest | 16-11-2026 | 18-11-2026 | Dev and QA |
| Regression on final build | 19-11-2026 | 20-11-2026 | QA team |
| Test summary and sign-off | 23-11-2026 | 23-11-2026 | QA lead, product owner |

# 9. Risks and how we handle them

What could stop or slow down testing? For each risk, write the impact and what you will do about it.

| Risk | Impact | How we handle it |
| --- | --- | --- |
| Build reaches QA late | Less time to test | Test high risk features first. Agree a cut-off date for new changes. |
| Payment sandbox is down | UPI autopay cannot be tested | Keep mock responses ready. Book a fixed test slot with the payment team. |
| Not enough real devices | Device specific bugs are missed | Use BrowserStack for extra devices. |
| Requirements change mid cycle | Test cases go out of date | Freeze scope after sprint planning. Update test cases the same day. |

# 10. Deliverables

What will QA hand over, and when? Link to where each item is stored.

| Deliverable | What it contains | When |
| --- | --- | --- |
| Test plan | This document | Before testing starts |
| Test cases | Steps, test data and expected results, linked to user stories | Before execution |
| Bug reports | One report per bug, using the TesterPath bug report template | During execution |
| Daily status | Cases run, passed, failed and blocked, plus top open bugs | Every day of execution |
| Test summary report | What was tested, results, open bugs, go or no-go advice | End of testing |

# 11. Defect process

Say how bugs move from "found" to "closed", which tool you use, and how severity is set.

Bug life cycle: New → Open → Fixed → Retest → Closed. If the retest fails, the bug goes to Reopened and back to the developer. Example: Bugs are logged in Jira. A short triage call happens every day at 11 am to set priority and owner.

| Severity | Meaning | Example from the food app |
| --- | --- | --- |
| Critical | Crash, data loss, or a main flow is blocked. No workaround. | Payment is taken but the order is not created |
| Major | A key feature works wrong, but there is a workaround. | Reorder adds the wrong item size. User can fix the cart by hand. |
| Minor | Small problem. The feature still works. | Scheduled time shows in 24-hour format on one screen |
| Trivial | Looks only, like a typo or spacing issue. | Spelling mistake on the offers banner |

# 12. Sign-off

The people below agree that testing is complete and the release can go ahead.

| Name | Role | Date | Signature |
| --- | --- | --- | --- |
|  | QA lead |  |  |
|  | Development lead |  |  |
|  | Product owner |  |  |